## Sheet1
Project Type | Chargecode | Project Name | Implement date | Current State | Scope Detail | Time Detail | Cost Detail | Progress | Planned Budget | Actual Budget | Owner | Status
Project | I606 | DDAP For Branch | 2025-09-26 | Implemented | PVT Done and Have Defer on 26/9 | - | Just Pass Deepdive On Process to PO | 100% | 966000 | 960000 | SONG | Green
Project | I522 | DDAP For Wealth | 2025-09-26 | Implemented | PVT Done and Have Defer on 26/9 | - |  | 100% | 994000 | 900000 | SONG | Green
Project | I522 | RMX Pitchbook | 2025-09-26 | Imp in Progress | Pentest Finish with 1 low and will fix later | - | Pentest Vender PO received | 90% | 0 | 0 | SONG | Green
Project | I470 | Preventive | 2025-10-17 | Imp in Progress | Clarify all issue and in-progess UAT | - | Just Ready for PO( User on Processing) | 90% | 1246000 | 691740 | SONG | Green
BAU | AP1739 | Wealth CardX | 2025-11-21 | Design | Already Clear Requirement but wait for UDP(datax+edw) | on Risk | BAU | 20% | 0 | 0 | SONG | Amber
BAU | AP1739 | Ismart EFCD Migrate | 2025-12-12 | Design | Discuss with ismart for scenario | - | - | 10% | 0 | 0 | SONG | Amber
BAU | AP1739 | VVIP Flag | - | Req | Already Send Slide to user waiting for meeing With P'Jai | - | - | 10% | 0 | 0 | SONG | Amber
BAU | AP1739 | Virtual Teller | - | Ideation | User Already use v teller via ipad | - | - | 50% | 0 | 0 | SONG | Green
Project | I567 | Wealth Stella | 2025-12-12 | Develop |  | - | - | 50% | 0 | 0 | SONG | Green